Minutes of the meetings held on 18th September, 2017

Present;  	Peter Cowx,  David Pain, Christopher Prentice, Pauline Smith, Peter Smith & Cliff Davies.

Apologies;	Julia Blake & Yoshi Nishio

- The minutes of the meeting held on 17th August, 2017 were accepted.

Actions arising:		See item 5 below

- Update on Roger Baker

PC advised that Roger had been released from hospital a little over a week ago and was now recuperating at home.   Those present, on behalf of the entire SG, send Roger their best wishes for a speedy return to full health.

- V&O Consultation

The follow-on survey has now been closed and while only a minority of those approached chose to expand on their initial responses, their feedback will be added to the evidence base for use in preparing the Plan policies albeit the impact is likely to be minimal.

- Draft Policies

Following the meeting of 17th August CD had forwarded both draft versions of the ‘plain English’ policies to BSP and then met them immediately thereafter to discuss same.   It was evident from the points raised that significant reworking would be required, and BSP have been tasked with doing this while also adding an extra “open space” policy – CD’s Email update of 24th August refers.

It had been hoped that the reworked policies would be ready in time for the meeting, but prior to the meeting CD confirmed that BSP holidays had significantly delayed things – CD to progress

Post meeting BSP confirmed the amended policies will be available for 2nd October.   CD to progress w/c 25th September.						Action CD

At the last meeting CD had requested all group members to comment on YN’s draft policies having first assessed these against the V&O survey results & the Locality recommendations annexed to the S&V meeting minutes.   Instead all group members are requested to adopt the same process once the reworked policies are issued.			Action ALL

PS suggested that a policy should be added to cover economic activity, but CD pointed out that the business survey had not identified any immediate requirement that would necessitate land use, and the subject would therefore be dealt with through a strategic objective.

- Ongoing Tasks

These all relate to the production of the Plan and were annexed to the skeleton issued prior to the meeting of 17th August.   The current position on same is as follows:

PS		Report on aging population - ongoing:   The intended ‘few pages’ has now expanded to take account of feedback from S&V, and a revised completion date of 29th inst agreed.									Action PS

CA’s	Following the meetings with S&V and BSP, authors were requested to not only amend their reports to include both positive & negative features of their areas but, more importantly now, to highlight features that serve to underpin our policies - e.g. chalk springs, important buildings, etc – ongoing:   NB: Please use the ‘plain English’ drafts pro-temp, with a revised target completion date of 29th inst.				Action CA authors

BSP	Produce drawings – ongoing.   Roger having resigned due to ill health, this task was transferred to BSP, and they expect to issue the initial results w/c 18th inst.

Action BSP

JL/DP	Landscape CA – complete?   DP tabled a hard copy of the revised appraisal at the meeting, and CD asked that the electronic version be forwarded for editing and/or record purposes.

YN/CD	Produce Plan outline – ongoing:   As YN is currently unavailable; CD will work on this pro-temp.

- Progress On Key-Lists

Little meaningful progress had been made on this, and SG members were again asked to provide their proposals for ‘designated green space’ & ‘community assets’ to be identified and listed within the Plan.   Similarly, feedback is still required on footpaths in need of repair, particularly cross-country paths.

There was some concern about a perceived ‘scatter-gun’ approach, but it was pointed out that duplication was far preferable to omission when it comes to editing the feedback & compiling definitive lists.

- AOB

- Local Plan Update:		PC & CD agreed to attend the Seminar on 19th inst.

Post meeting CD provided an Emailed over view of the presentation – Email of 20th September refers.

- Community Awareness:	The need for a campaign to raise awareness within the community of both the purpose of the Plan and how our policies achieve this was raised at the last meeting.   To make this as interesting as possible it was agreed to frame it within a historical context with contributions from those that have produce relevant briefing papers for the Plan – i.e. JL/DP & PS plus Oliver Green on farming if he is willing.

The meeting will be held on Monday 30th October at the Village Hall if available [CD to confirm], and should be given maximum publicity.   		Action CD

PS also confirmed that JL/PS were planning parallel ‘more intimate’ meetings with the aim of involving still more; and CD requested that a proposed format be issued for consideration by the group.						Action JL/PS

- Date of next meeting

TBA

Cliff Davies

23rd September, 2017