Minutes of the meetings held on 17th August, 2017

Present;  	Julia Blake, Peter Cowx,  Jonathon Loose, Yoshi Nishio, David Pain, Christopher Prentice, Pauline Smith, & Cliff Davies.

Apologies;	Peter Smith

- The minutes of the meeting held on 20th July 2017 were accepted.

Actions arising:		CP/PS;   overview of ‘Stakeholder Survey’ – complete, draft report issued at meeting.

JB/PC/CD/RT;   continuing, all have been written but are currently being reviewed in light of BSP comments, and meeting with S&V yesterday

JL/DP;   countryside appraisals – continuing, appropriate extracts need to be formatted to required pro-forma.

- Update on Roger Baker

PC advised that Roger’s operation had gone well and he is now in recovery mode and showing marked signs of improvement.

The need resolve how we produce the requisite maps is still ongoing as we await Sharon at BSP to confirm that the original base drawing is adequate for editing purposes – see XYZ below.   Our backup remains NW as he has the necessary software and will assist in any way that he can.

Action CD/PC

- Feedback from S&V meeting

PC/PS & CD gave a brief report on their meeting, and written minutes will be circulated in due course.

Post meeting: minutes attached.

- V&O Consultation

Conduct follow-on survey is continuing, but feedback received thus far has not produced any meaningful changes, with the consequence that there is unlikely to be any impact on the policies, but this will be reviewed on completion			Action : YN/CD/ALL

After discussions with both BSP and S&V, the closeness of the survey results on key objectives indicate that no prioritisation is necessary, but the expectation is that priority will therefore be given to [say] housing rather than infrastructure, but it now a matter of our choice rather than any expectation.

- Draft Policies

Prior to the meeting CD had drafted/issued ‘plain English’ policies, and YN had issued a further structured revision for consideration by the group and BSP.   Group to consider, and comment on, the drafts taking into account the advise given by S&V – see separate minutes.

Action CD/YN/ALL

YN also suggested that, in his editorial capacity, he expand on the initial Plan outline to provide a better indication of its structure and CP volunteered to assist in this.

Action YN/CP

The matter of how to deal with such topics as the aging population and highlighting the Parish’s unique features were aired at length at the meeting with S&V and the key ‘needs’ are given in the separate minutes to that meeting.

Given the importance of the Plan policies, CD requested that all members of the group comment on YN’s draft having first assessed these against the V&O survey results & the Locality recommendations annexed to the S&V meeting minutes.

- Ongoing Actions

These all relate to the production of the Plan and were annexed to the skeleton already referred to.   At this stage the immediate requirement was to complete those tasks referred to in 1-above, and to circulate for comment with  a general target date of 14th August for doing this, other than the Characterisation appraisals where the target date is 7th August - please note, when the time comes such comments should be restricted to correcting errors of fact and/or omission only.						Action ALL

One area of concern in respect of the ongoing actions is how best to deal with those tasks originally delegated to RB.   The first priority was to determine what progress RB had already been made and only then could a decision be made on what if anything needed to be reallocated to other members of the group.	This will form part of the feedback from 2-above.

- AOB

A meeting has been arranged with Bluestone for Wednesday 23rd inst at 10:00am to discuss further tasks to be delegated to them.

- Date of next meeting

23rd September at 10:00am, at The Manor

Cliff Davies

22nd August, 2017